## Sheet1
AUK Institutional Strategic Plan Operational Map 2025-2026
1. To develop a university campus that meets the needs of current and future students, faculty, and staff as well as serves as a model for higher education across Kurdistan
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Proceed with the implementation of a Master Utility Plan that is designed to accommodate campus expansion | CoE, CSD | To prepare the campus for new buildings and landscape. The infrastructure must be in place before further construction. | Collect offers for the construction of the main utility lines plus repairing the sewer treatment plant. | Short-term: Finish the bidding and permitting process. Long-term: Finish the construction, furnish it, and prepare it to be connected to the utility systems of new constructions. New campus roads, parking, and bike routes need to be built. | Finish about 80% of the construction, projected completion by fall 2026. | Master Utility Plan: Construction to start in April 2026 and led/overseen by AUK Resident Engineer. | Design and construction costs; AUK's Resident Engineer. | 50% of the plan has been implemented
Complete the design for and begin construction on “Building B” | CoE, Resident Engineer | To create an academic and civic hub designed to house the Conference Center, College of Engineering, and College of Medicine; the building will integrate learning environments, LEED certification sustainable principles, and community spaces. | Set a full plan for the construction of Building B, with alignment with LEED standards. | Short-term: The detailed design package to be ready by the end of the year and the rest of the tender package to be ready for construction by the end of January 2026. | The detailed design and the tendering package are ready and the collection of offers for construction is started. | AUK's Resident Engineer to meet with the designers on a regular basis; benchmarks and timelines to be established and followed. | Design and construction costs; Resident Engineer. | 75% of the design has been done; updates provided to BoT for review and approval.
Implement green initiatives including water and waste recycling to further campus sustainability efforts and promote environmental awareness | Legal Office | To promote AUK as the leading actor in the region advocating for human rights and the Universal Sustainable Development Goals (SDGs). | Submit report/s of AUK's activities and projects relevant to human rights and SDGs to the Iraqi High Commission for Human Rights and other national and international agencies; campaign on and off campus for the UN SDGs, including inviting advocates to motivate campus; establish drinking water dispensers to avoid plastic bottles; put in place effective waste management policies and practices. | Seek national and international funds to support the SGDs initiatives in the Region; raise the communities’ awareness of the most pressing environmental issues and role the University and its community can take. | Conduct two campaigns; one on-campus and one off-campus; invite SDG advocates to AUK; submit reports of activities and projects concerning SDGs to Iraqi High Commission and other relevant agencies. | Surveys to monitor communities’ knowledge of environmental issues and the strategies/tools available to address these issues; report/s to relevant national and international agencies; 3. Number of international and national funds secured to support such initiatives. | Form a Task Force responsible for collecting data of AUK activities and projects to write report/s to national and international agencies evident AUK good governance; sufficient funds to conduct campaigns, student volunteers, and guest speakers. | The individuals of the Task Force have been identified. In pring, it will begin planning.
Implement green initiatives including water and waste recycling to further campus sustainability efforts and promote environmental awareness | CSD | To promote AUK as the leading actor in the region advocating for human rights and the Universal Sustainable Development Goals (SDGs). | Submit report/s of AUK's activities and projects relevant to human rights and SDGs to the Iraqi High Commission for Human Rights and other national and international agencies; campaign on and off campus for the UN SDGs, including inviting advocates to motivate campus; establish drinking water dispensers to avoid plastic bottles; put in place effective waste management policies and practices. | Seek national and international funds to support the SGDs initiatives in the Region; raise the communities’ awareness of the most pressing environmental issues and role the University and its community can take. | Conduct two campaigns; one on-campus and one off-campus; invite SDG advocates to AUK; submit reports of activities and projects concerning SDGs to Iraqi High Commission and other relevant agencies. | Surveys to monitor communities’ knowledge of environmental issues and the strategies/tools available to address these issues; report/s to relevant national and international agencies; 3. Number of international and national funds secured to support such initiatives. | Form a Task Force responsible for collecting data of AUK activities and projects to write report/s to national and international agencies evident AUK good governance; sufficient funds to conduct campaigns, student volunteers, and guest speakers. | Separation of cardboard began in September 2025, amounting to five 2-ton truckloads sent to waste management company. Starting January 2026, records will be maintained for all collected and dispatched materials. Placed four recycling bins in each kitchen in the female residence facility—paper, organic, plastic, and general waste.
Implement green initiatives including water and waste recycling to further campus sustainability efforts and promote environmental awareness | CoE, CSD | To establish a sustainable campus environment that reduces resource consumption, minimizes environmental impact, and fosters a culture of environmental responsibility among students, staff, and the broader community. | Connect the wastewater system from the AUK building to the wastewater treatment plant to treat and reuse water for irrigation purposes; collect and store rainwater, ensuring its reuse for irrigation; construct a central garbage room designed specifically for segregating different waste streams; provide recycling bins across campus buildings to encourage proper waste segregation at the source. | Reduction in the use of freshwater resources for irrigation; higher recycling rates, cleaner campus environment, and improved student/staff awareness and participation in sustainability practices. | Connection of the AUK building’s wastewater system to the treatment plant is completed; the wastewater treatment plant is fully operational and providing treated water for irrigation; a central garbage room, designed for segregating different waste streams, is constructed and in use; recycling bins are installed and distributed across campus buildings; waste segregation process is active, with staff and students participating in proper disposal practices. | Waste Audit Reports; observation & compliance checks. | Funding for the construction of the garbage room and the furnishing of buildings with recycling bins. | The male dormitory, scheduled to open Spring 2026, is furnished with recycling bins and solar power system as part of the Leed-certified sustainability initiatives.
Establish a living-learning lab dedicated to solar energy via the installation and management of solar panels as a clean alternative energy and as an educational lab for students and the community | CoE, CSD | To reduce the fixed cost of the diesel generators and implement cleaner energy sourcing. To provide the students with a living -learning lab dedicated to solar energy to demonstrate the impact of renewables on the operational and environmental costs of the University and region. | Tender process is finished and contractor is selected. WSU is contracted to overview the project. The solar panels will be installed on MB and FRF in addition to the car parks. | Short-term: Produce plans for installing the solar panels and battery packs on Mustafa Barzani Building, Female Residence, and employee parking lot. Long-term: Calculate amount of energy generated, diesel saved, reduction in costs, noise and air pollution. Students to manage this living-learning lab, collect and analyze data on energy usage, and devise strategies for community education. | The solar system installation is 90% finished. Full completion in August 2026 as per DoS timeline. | AUK Resident Engineer and WSU to monitor the process; final construction plans package completion rate. | DoS funding. | The construction phase has commenced and is expected to be completed by July 2026.
Develop programming and social structures that ensure the Male Residence Facility becomes a living-learning community | OSA | To establish the Male Residence Facility as a welcoming and convenient on-campus accommodation for male students that creates a supportive and engaged community. | Organizing regular social activities; creating leadership opportunities as Resident Assistants; establishing sports community. | The Male Residence Facility will be a welcoming home where students feel they belong. Students will take part in activities and events, make connections, and over time, the residence will grow into a lively, closely-linked community. | The Facility will only be open for one semester (spring) by end of reporting year; a few programs will be implemented. | Level of engagement of students in community-building activities (sports, volunteerism, etc.); students' feedback on the MRF experience. | N/A | The Male Residence facility will open Spring 2026; the Facility's Administrative Assistant has been hired.
Develop and implement an IT plan focused on campus cybersecurity and infrastructure protection | IT | To provide a more secure and reliable technology environment by strengthening cybersecurity measures and protecting campus infrastructure, ensuring the continuous availability of IT services. | 1. Webex Platform Implementation: Configure Webex tenant settings and integrate with Active Directory; establish security and compliance policies (recording, retention, MFA); train staff and faculty on effective usage; monitor adoption rates and user feedback for continuous optimization. 2. Cybersecurity Enhancement – Phase II: Deploy and configure FortiSIEM for centralized log management and threat detection; integrate FortiSIEM with existing firewalls, servers, and endpoints; implement enterprise-grade antivirus across all devices; conduct penetration testing and security awareness training for staff. 3. Data Center Modernization – Phase I: Assess current workloads and migrate them to the upgraded HP server; configure server redundancy, virtualization, and backup systems; test failover and disaster recovery scenarios; document new infrastructure and train IT staff. 4. Surveillance Infrastructure Overhaul: select a new camera brand and NVR solution; redesign camera placement to maximize coverage; install additional cameras to cover blind spots and sensitive areas; integrate the new cameras and NVR with central monitoring systems. 5. Interactive Classroom Technology Deployment: Complete installation of interactive classroom screens; standardize configuration across all devices for unified experience; provide faculty training for effective use of interactive features; establish maintenance and update schedule for hardware/software. 6. Enterprise Ticketing & Task Management System: Configure categories, SLAs, and escalation workflows; train staff on ticket submission and tracking; monitor resolution times and continuously improve processes. 7. Access Control Expansion: Procure and install access readers for labs, storage rooms, and restricted areas; integrate readers with central access control software; define and enforce user access policies by role; periodically audit access logs and update policies as needed. | 1. Webex Platform Implementation: Short-term: Webex configured and fully integrated with directory and security policies; staff trained; smooth adoption across departments, and Long-term: Webex becomes the unified collaboration platform for the university, reducing reliance on third-party tools and improving communication efficiency. 2. Cybersecurity Enhancement – Phase II: Short-term: FortiSIEM deployed and generating centralized security alerts; antivirus installed on all endpoints, and Long-term: A mature cybersecurity posture with proactive monitoring, reduced incidents, and strong compliance with international standards. 3. Data Center Modernization – Phase I: Short-term: Primary HP server upgraded with improved performance and tested for reliability, and Long-term: A scalable, resilient data center architecture supporting future workloads, with phased upgrades to full redundancy and cloud integration. 4. Surveillance Infrastructure Overhaul: Short-term: New cameras and NVR installed; optimized coverage eliminating blind spots, and Long-term: A modern, scalable surveillance system integrated with centralized monitoring, ensuring campus-wide security and future expandability. 5. Interactive Classroom Technology Deployment: Short-term: All classrooms equipped with functional interactive screens; faculty trained to use them effectively, and Long-term: Smart classrooms become a standard, enhancing teaching quality and enabling digital transformation in education delivery. 6. Enterprise Ticketing & Task Management System: Short-term: Ticketing platform deployed; workflows and SLAs in place; staff trained, and Long-term: A culture of accountability and efficiency with data-driven IT operations, enabling proactive planning and continuous improvement. 7. Access Control Expansion: Short-term: Access readers installed and integrated into security systems; user policies enforced, and Long-term: A comprehensive campus-wide access control system safeguarding labs, storages, and sensitive areas with audit-ready logs and scalable expansion. | 1. Webex Platform Implementation: Full deployment completed across related departments; adoption rate 60% among staff and faculty. 2. Cybersecurity Enhancement – Phase two: FortiSIEM operational, integrated with all critical systems 100%; antivirus solution standardized and monitored across 100% of endpoints.3. Data Center Modernization – Phase one: HP main server upgraded and in production with redundancy enabled; 60–70% of workloads migrated to the new infrastructure; documentation and staff training finalized. 4. Surveillance Infrastructure Overhaul: Phase I rollout complete with new cameras and NVR installed; at least 75% of priority zones covered with improved visibility; central monitoring system integrated and functional. 5. Interactive Classroom Technology Deployment: 100% of classrooms equipped with interactive screens; support/maintenance system in place for ongoing reliability. 6. Enterprise Ticketing & Task Management System: Ticketing platform in full use across IT; 90% of IT requests routed through the system; SLA compliance metrics being tracked and reported monthly. 7. Access Control Expansion: Access readers installed in all labs and high-priority storage areas; policies configured and role-based access enforced; quarterly audits established to review access logs. | Full deployment of Webex Platform; Usage rates meeting targets; FortiSiem full implementation; completion of Data Center server upgrade; upgrade of surveillance with cameras; interactive classroom tech deployment completed; Ticketing & Task Management System deployed; security access mechanisms installed. | 2025-2026 Budget., some funded via DoS. | 1.Webex Platform Implementation: done. 2.Cybersecurity Enhancement – Phase two: in progress. 3. Data Center Modernization – Phase one: still investigating vendors. 4. Surveillance Infrastructure Overhaul: NVR has been ordered and the coverage of campus cameras is under testing. 5. Interactive Classroom Technology Deployment: in progress. 6.Enterprise Ticketing & Task Management System: in progress. 7. Access Control Expansion: sample has been installed in Finance and under testing.
Raise awareness of the Smoking Policy and promote the values of a smoke-free campus | OSA | To implement programming to promote the values of a healthy lifestyle, including reduction/cessation of smoking. | Hold awareness-raising campaign in accordance with the implementation plan, which includes developing various promotional materials, organizing small-scale events, online promotion, shows on Leopard Radio, facilitating student-led debates and workshops. Continue after initial month with follow up conversations/workshops/events. | Students recognize and respect designated smoke-free zones and campus policies; policy violations decrease significantly in areas where clear signage is displayed; students actively engage in awareness events and campaigns promoting a smoke-free environment. | The updated smoking policy is fully implemented across the campus; assessment mechanisms of enforcement are being implemented and data assessed for compliance. | Number of students attending the student-led debates; number of students attending workshops; number of reported violations; measurements of students' understanding of a healthy lifestyle. | N/A | The Smoke-Free Campus Awareness Campaign was in September. In total, six events were held, including workshops, a student-led debate, a radio program, a social media awareness campaign, and three on-campus awareness events. Overall, 366 on-campus participants and an online reach of 1,128.
2. To offer academic programs that are designed to meet market demands while exemplifying the best international standards
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Review current bachelor’s curricula and revise plans of study to ensure they reflect up-to-date knowledge and skills that match market demands | CoN | To ensure that the nursing bachelor’s program meets accreditation requirements, reflects evidence-based, emerging practice in nursing, satisfies stakeholders (students, employers, health industry), and graduates are prepared for current and future healthcare system needs. | Document and data gathering; self-study preparation; internal & external Program Review; feedback collation and analysis; revision & implementation; initial accreditation visit; post-visit follow-up. | Short-term: External/internal review conducted; reviewer reports received. Long-term: Accreditation granted (initial) or strong readiness. | All recommendations from accreditation decision addressed; continuous improvement plan up and running. | External review reports/findings; resource audit: labs, clinical sites, faculty credentials; timelines / deliverables: whether each phase completed on schedule. | External reviewers/consultants; printing /digital repository or document management system costs; miscellaneous logistics (meetings, site visit hosting). | A program review was completed in November 2025, and the findings were incorporated into curriculum revisions and accreditation documentation. The CoN is actively preparing for the NLN CNEA initial accreditation site visit scheduled for February 2026.
Review current bachelor’s curricula and revise plans of study to ensure they reflect up-to-date knowledge and skills that match market demands | CoAS/Design | To develop a relevant design curriculum that reflects contemporary commercial and social issues. | Self study report; program review and its feedback; revision of curriculum based on recommendations. | The alignment of the curriculum to current and future market needs while providing an adaptive, flexible and more in-depth engagement within specific design tracks. | Final draft of the revised program. If deemed substantive, then approval of BoT. | Self study report, program review process, revised plan of study, new marketing materials to brand program and enhance recruitment. | Faculty and dean support. | The academic program review self study report has been submitted to the OIEP office and the review process will take place during the second week of Febraury.
Review current bachelor’s curricula and revise plans of study to ensure they reflect up-to-date knowledge and skills that match market demands | CoB | To update the B.A in Business Administration to improve graduate employability, relevance of the degrees, stakeholder satisfaction, and regional competitiveness of the program. | Gather market intelligence specific to employer needs, industry trends, required skills (technical, soft skills); survey alumni to identify gaps in workplace needs; conduct research on programs at peer institutions; draft new study plan. | Short‑Term: Audit of existing curricula for all three specializations; market intelligence; draft of new program. Long‑Term: Assess outcomes on course and program levels for improved employability, higher workplace satisfaction; increased enrollment due to program relevance. | Market intelligence reports completed; draft revision of curriculum; faculty training for new tools/technologies underway; advisory board active. | KPIs: Student performance in new courses; employer/alumni satisfaction surveys; enrollment numbers; feedback from students on course relevance and satisfaction. | Curriculum review committee; market analysis; survey support. | Draft completed. To be presented to the BoT for approval.
Investigate the possibility of offering graduate certificates to meet the life-long learning needs of alumni and the professional community | CoN | To develop a proposal for a graduate certificate program in nursing, incorporating feedback from stakeholders and aligning with accreditation standards. | Curriculum design; stakeholder engagement; accreditation and compliance; financial planning; program proposal development. | Short-term: Completed curricular framework; evidence of market need and ability to accommodate graduates. Long-term: Approved program proposal ready for submission to NECHE. | Finalized program proposal. Need for NECHE approval. | Curriculum approval documents; stakeholder feedback reports; budget and financial planning documents; proposal for NECHE and nursing accreditor. Need support from MoH for accommodation of graduates. | Faculty for curriculum development; administrative support for proposal development. | A feasibility study has been completed. Development of the graduate certificate curricular framework is underway, with benchmarking conducted against comparable programs at peer universities.
Explore the applications of AI in the enhancement of teaching and learning | Library | To integrate AI-driven tools and literacy programs into library services that support teaching, learning, assessment, research, and student success. | Develop and deliver AI literacy workshops for students and faculty, focusing on ethical use, effective prompt design, and evaluation of AI outputs; pilot AI-driven research support tools such as chat-based discovery in WMS, citation checkers, and text summarization services; collaborate with faculty to integrate AI modules into information literacy and research skills sessions; support academic staff in applying AI to teaching, including lesson planning, assessment design, and feedback automation. Curate and maintain a dedicated AI resource hub with guides, policies, FAQs, and recommended tools. | Short-term: Students and faculty trained in AI literacy, increased adoption of AI tools for research and teaching. Long-term: AUK positioned as a leader in responsible and ethical AI integration in higher education within the region. | Deliver a minimum of three AI workshops for students and faculty to build institutional awareness and competency in AI literacy; develop, publish, and promote AI usage guidelines for library users to support responsible and ethical adoption of AI tools. | Attendance and feedback from workshops; usage statistics for AI library guides and tools; surveys of faculty and students on AI awareness and adoption. | Library staff training in AI tools and pedagogy; budget for AI software trials/ licenses. | AI literacy content has been incorporated into existing Information Literacy Sessions. Independent AI workshops are pending until the University’s formal statement on AI usage is finalized and approved. Development of AI-driven functions in the library system (e.g., chat-based discovery and new WMS modules) is paused pending the arrival and implementation of scanner.
Explore the applications of AI in the enhancement of teaching and learning | CoN | To develop and implement AI-driven clinical scenarios in the NSSL, enhancing realism and interactivity. | AI selection tool; faculty training; integration planning; scenario development and implementation. | Short-term: Faculty trained in AI tools. Long-term: AI-driven simulations fully integrated into the curriculum. | Successful implementation of AI-enhanced simulations; positive feedback from students and faculty; data indicating improved learning outcomes. | Feedback surveys from students and faculty; comparison of learning outcomes before and after AI integration. | Nursing Faculty; Lab Coordinator; Budget for faculty AI Training workshop. | A Clinical Simulation Training Workshop was conducted in August 2025, which included AI integration in scenario development. Faculty are currently incorporating AI-enhanced simulation scenarios into their courses.
Establish inter-library loan agreements with regional universities | Library | To broaden access to academic resources by connecting AUK students and faculty with regional library collections. | Identify potential partner universities in the region; negotiate and sign MOUs; develop standardized request/fulfillment procedures; train library staff and promote service to faculty and students. | Short-term: Signed agreements with at least 3–5 partner institutions. Long-term: Increased student and faculty satisfaction with research resources, measurable through usage and feedback. | 3 agreements signed. | Number of agreements signed; number of inter-library loan requests fulfilled; faculty/student survey feedback. | Library staff time for coordination; costs for transport of any physical copies. | With the launch of WMS, the Library has targeted subscription in OCLC’s LVIS (Library Very Interested in Sharing) program to support interlibrary loan of electronic resources. At this stage, AUK library is not yet able to join LVIS, as the Library must first be established as an active supplier. Progress is dependent on OCLC completing the demo, as well as the required training and configuration sessions.
Found student clubs and chapters with international disciplinary/professional organizations and that are aligned with the curricula of the academic programs | COAS/CSIT | To build connections with international student chapters to enhance professional development, global exposure, and professional alignment with CSIT curricula. | Apply for chapters such as Women in Cybersecurity; support the CSIT student club (HacAUK), and link their activities with academic and career goals. | Short-term: Secure at least one international chapter to support CSIT student club. Long-term: Expand to multiple chapters, enhance student engagement, and raise the international profile of CSIT students. | CSIT establishes connections with relevant chapters or clubs that are aligned with an international professional association. | Meeting minutes; progress reports; subscription to their respective professional/international association. | CSIT Student Club; Association-affiliation fees. | Applications have been submitted to several professional and student chapters. Geographic restrictions hinder some organizations from considering applications from Iraq.
Foster faculty research and professional development through local, regional, and international collaborations | COAS, Gen Ed, CELT | To improve recruitment and retention of faculty through implementation of robust program of professional development. | Organize workshops, lectures, invite guest speakers, etc. | Making international contacts with expert trainers. | Gen Ed establishes connections with local schools and universities. | Keeping track of contact progress with logs and list of potential interested participants | Gen Ed faculty/CELT: Budget for transportation to schools and universities; support for workshops and PD activity. | Chair of Gen Ed moderated a panel discussion on English Language Education in Kurdistan at a conference organized by the MoHESR. Made some contacts with U of Dohuk.
3. To offer expertise and programming to the community to foster a culture of life-long learning and position AUK as a visible player in providing quality and accessible education in Iraq and beyond
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Assess the market research to gauge the feasibility of providing certificate programs and establish satellites in Mosul and Erbil | CAPA | To develop a presence in Erbil and Mosul with the objective of expanding products, market reach, and revenues. | Launch "She Leads" in Erbil leveraging DoS funds with implementing partner, Salahaddin University; hire staff locally to run the program; establish IH Duhok satellite; expand outreach to establish market needs and design new products and services accordingly. | Partnership agreement established with Salahaddin; staff hired and trained; rooms furnished; partnership with a corporate entity signed; a minimum of 50 students recruited. | CAPA program established and running; program selection based on market needs. | Staff hired and working independently; students recruited; partnership(s) in place; center offering quality educational experience. | 2 staff and volunteers recruited; furniture and operational support for updating of spaces; start-up costs for staff and equipment. | She Leads was launched in Erbil and graduation event in partnerhsip with Salahaddin Univeristy. Continued search for more permanent physical space in Erbil.
Work with regional universities to expand collaborative academic, co-curricular, and extra-curricular efforts | CoAS/CSIT | To strengthen collaboration with regional universities through the hosting of events that promote innovation, knowledge exchange, and industry engagement. | Organize the second regional coding hackathon as a tech fair with coding competitions, tech panels, project expos, and tech company participation, while inviting regional universities to attend and participate. | Short-term: Successfully host the tech fair with participation from regional universities and industry. Long-term: Establish the event as an annual platform for collaboration, expand partnerships, and position CSIT as a regional leader in technology-driven initiatives. | The successful completion of the first Tech Fair with participation from regional universities and industry. | Event attendance, participant feedback, quality of student output. | Event organization; costs for event logistics, travel, and materials; Sponsorships. | The second regional coding hackathon is planned for April 28, 2026, with regional universities invited to attend and participate.
Further develop programming at Leopard Radio to engage various regional audiences and market the University | CoAS | To continue to provide an English-language education and entertainment platform that will appeal to the regional audience while promoting the University. | Continue to develop a balanced schedule that includes educational programs (e.g., English language, health, history, scientific developments) and entertainment (e.g., music, interviews with local personalities, community stories); feature local experts, influencers, and community members creating a stronger regional connection; use social media, local events, and community partnerships to promote the station's programming and reach new listeners. | Create higher levels of listener participation, feedback, and interaction through call-ins, social media; bring listeners from different demographic groups, geographic areas, and cultural backgrounds; enhance station's reputation as a key regional media outlet, leading to potential sponsorships. | Develop and complete 5 to 7 regular programs; continue work on the live show to improve quality and audience interaction; improve music content; maintain a regular broadcasting timetable for all programs. | Analyze audience data: Number of listeners, their demography, and their feedback on the quality of our programs. Create and analyze data from student surveys to gauge listener satisfaction with content. | Work study students. | In Spring 2026, plan to increase the number of programs to about 10 regular programs, two of which will be live shows; may add a third. Hiring additional work-study students, bringing the number to nine. Total number of students trained in journalism and media production will be about 550 at end of semester.
Expand the Library membership program to provide more of the community with access to the resources | Library | To strengthen AUK’s role as a community hub by offering expanded access to external users. | Revise membership policy; launch outreach campaign ; introduce tiered membership levels with digital and physical access options; train staff in membership services. | Short-term: Increase membership by 20% year-on-year. Long-term: Establish the library as a central knowledge resource for the Kurdistan Region. | Expanded membership program with documented growth. | Number of new memberships; usage statistics (circulation, database logins); community feedback surveys. | Marketing budget for outreach campaign; IT support for expanded access systems. | Completion of key WMS functions remains pending, including scanner implementation and API activation. The scanner is expected to be delivered in February, followed by the launch of related APIs. Expansion of membership and related services cannot proceed until these system functions are fully operational. In parallel, the Library has provided access to resources for Zirka Prison through book donations and has initiated plans for a “Letters from Prison” project to document inmate stories. This initiative is intended to expand resource support to additional prisons across the region.
Devise a system for the measurement of AUK’s impact on the community in respect to economic, educational, and professional contributions | CAPA | To identify a tool/system that measures impact, adapt to AUK's context, develop local capacity and logistics to implement. | Research similar systems in peer institutions; identify a system and begin testing; train the staff to adopt and implement. | Experts assisting in researching systems and adaptation to AUK context; system adapted and deployed; staff ready. | System ready to be deployed. | System ready to measure "impact". | Developing or acquiring tool for measurement. | Search for the tool in progress. Challenge is lack of staff to dedicate to project. Impact metrics established within VNG, GIZ, and DoS grants.
Support the public and private sectors in creating policies for good governance and the introduction of best legal practices | Legal Office | To help foster the principles of good governance: transparency, accountability, and integrity | Inform the public and private sectors as well as NGOs of the services available through the Legal Office. | Short-term: Assist public and private sectors as well as NGOs to develop comprehensive policies that ensure all organizational decisions follow transparent, documented processes with clear accountability chains. Long-term: Legal Office to accommodate requests to help review policies with the aim of fostering the principle of good governance. | Ensure that government offices, private entities, NGOs in Duhok are aware of the services offered to support and assist the development of policies, procedures, and practices. | Number of requests for support received by the Legal Office; satisfaction survey for external entities using services. | N/A | Although technical and advisory support was continuously offered to KRG by AUK, no formal requests for policy development were received. Discussion with Department of Foreign Relations halted as DFR unable to fund project.
4. To recruit students reflecting the profile of those most likely to succeed at AUK and ensure that no student be denied access to an education due to an inability to pay
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Use the profile of “the student most likely to succeed” to identify target schools in Mosul, Erbil, and beyond | ARD | To apply the ideal student profile to guide strategic recruitment and outreach toward schools likely to produce applicants with a high potential for success at AUK. | Analyze historical data to identify high-yield schools aligned with the ideal student profile; update the recruitment plan to prioritize these schools; implement outreach initiatives: school visits, campus tours, relationship-building with school administrators; scholarship offerings for qualified applicants. Implement the event calendar that includes both visits to Mosul schools and on-campus events hosted for them, with active participation from academic departments in all recruitment activities; run a targeted social media campaign focused on reaching audiences in Mosul; strengthen relationships with Mosul school administrators by inviting them to AUK events such as the Collaboration Enhancement Event. | Attract qualified applicants who meet the ideal student profile. Increased awareness of AUK in Mosul and attraction of a higher number of applicants from this city. | Targeted recruitment plan implemented; implementation of all recruitment strategies targeting Mosul as outlined in the recruitment and event calendar plans, with active participation of all stakeholders (faculty, college managers, and recruiters); achieve measurable growth in the Mosul applicant pool compared with the previous academic year. | Comparative analysis of retention and First-Year CGPA rates for students from newly identified feeder schools. Number of visits, events, and campaigns conducted; stakeholder participation rates in events; increase in the number of Mosul new students compared with the previous academic year. | N/A | Completed.
Strengthen the cooperation of ARD and the Colleges in student recruitment initiatives | ARD, Colleges, Provost | To enhance cross-unit coordination in recruitment planning and execution at the institutional level. | Maintain and update one unified recruitment calendar that includes all school visits, academic department events, and the names and roles of all participants (recruiters, faculty, college managers, and assistants). Coordinate on application timelines, admissions requirements, and promotional messages to avoid inconsistencies; college collaborate on school visits, online info sessions, and recruitment fairs—with faculty and ARD staff co-presenting. | Strengthened faculty involvement and institution-wide coordination through a unified, transparent recruitment event calendar. | Event Calendar implemented and updated in real time; maximum possible number of school visits and campus events executed based on school availability; recruitment collaborations regularly discussed at Academic Council. | Event implementation rate (number and percentage of planned events completed); turnover rate of interested to applied to matriculated; college stakeholder participation rate at events. |  | Unified recruitment calendar completed, including visits to target schools; events scheduled in coordination with academic departments.
5. To provide students with the support structures and tools for their academic and professional success
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Identify the skill sets most needed to enhance students’ employability and design and deliver workshops to address these gaps | OSA/Career Services | To enhance student leaders' leadership skills, foster a sense of responsibility, and promote effective community engagement. | Through trainings, equip students with essential leadership skills and effective communication techniques, enabling them to lead their peers ethically and inclusively. Collaborate with academic and non-academic units to assist in developing and facilitating the training. | Incorporate Vector Solutions training packages "Wellness and Safety" and "Career Readiness and Personal Development"; develop and implement trainings in Project Management, Event Planning and Management, Marketing, and Social Media; develop guidelines for student-led activities. | Completion. | Number of students completing the trainings; pre/post assessment of the trainings; guidelines on student-lead activities are finalized. | Vector Solutions annual subscription (DoS). | Career Services staff member will start in April 2026. The work-study program shifted to OSA; nine work-study opportunities announced, resulting in 43 students participating.
Design and implement programming to increase mental health awareness and improve the well-being among all campus demographics | OSA | To normalize the concept of mental health and help-seeking and access to current services. | By June 2026, implement a comprehensive Peer Health Advocates program, conducting events focused on mental and physical health awareness, and measure impact through post-event surveys, satisfaction ratings, and participation rates; train peer health advocates to raise awareness and engage with community. | Peer Health Advocates program will be fully established and operational across campus; series of mental and physical health awareness events conducted; post-event surveys and participation metrics will show measurable engagement and positive feedback; indicators will demonstrate increased student awareness, knowledge, and interest in health and well-being initiatives. | Completion. | Total count of health-related events organized by PHAs; total student attendance across all events; number of workshops conducted; number of awareness campaigns; total awareness initiatives, including social media, posters, and on-campus campaigns. | In 2025-2026 budget. | The Peer Health Advocate program was initiated with the recruitment of 15 Peer Health Advocates. Health Promotion Services hosted five campaign initatives: Mental Health Awareness, Blood Donation Drive, Zawita Community Outreach (under CoN), Diabetes Awareness Event, No-Elevator Day. Overall, 1288 students participated in events.
Devise and implement strategies to grow student engagement in co-curricular and extra-curricular activities as well as social and sports events | OSA | To increase student engagement and leadership while fostering campus involvement, soft skills development, and a strong sense of school spirit. | Organize a student-led conference; create a student-led magazine; launch a female volleyball team; foster more student-led workshops. | Increased student participation in campus life; increased opportunities for teamwork and collaboration. | Completed. | Number of attendees from across Kurdistan's universities; redesign SG with new representative structures; number of student contributions to magazine. | Dedicated spaces and coaches for sports. | Four student-led workshops in Fall 2025 with 32 student participants and a 100% satisfaction rate. Total, 10 workshops were delivered to students, with 193 attendees and an 86% satisfaction rate. Spirit Day was approved and will start in Spring 2026. The student-led conference to be finalized with the MoHESR (prospective date is April 4). Female Volleyball team has 22 students; 8 training sessions to date.
Grow the “Change-Makers” program to expand channels for students to engage in community service | OSA | To create more opportunities for students to engage in community service, foster a strong community service spirit, and strengthen connections with local community service stakeholders in Duhok. | Reach out to NGOs, local companies, and community organizations to provide students with off-campus volunteering opportunities, establish partnerships, and promote hands-on community engagement. | Increased student participation in meaningful off-campus volunteering activities; stronger partnerships with local organizations; greater sense of community service spirit among students. | Completed. | Number of students participating in the Change-Makers program; number of beneficiaries in community activities; number of off-campus community service initiatives. | In the 2025-2026 budget. | The Change Makers program started in Fall 2025 with the recruitment and training of seven Change Maker leaders; organized two school visits with 15 AUK student volunteers, benefiting 80 students.
6. To recruit and retain faculty and staff who will contribute to the mission of the University
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Benchmark employee benefits across regional universities and identify additional benefits that may make AUK more competitive in the recruitment of faculty and staff | HR | To provide a competitive, equitable, and attractive benefits package that strengthens AUK’s position as an employer of choice in the region, improving recruitment outcomes and retention rates. | Conduct comprehensive benchmarking of benefits (health, retirement, education, work flexibility) across regional and peer U.S.-model institutions. Initiate negotiations with the health insurance provider to explore spouse coverage, dependent coverage options, and preventive care benefits. Launch employee focus groups & surveys to identify the top 3–5 most desired benefits and prioritize implementation. | Short-term: Deliver a formal proposal including spouse coverage and new benefit recommendations. Long-term: Achieve higher staff/faculty satisfaction scores (>80% satisfaction in annual OIEP survey). | Benchmark report finalized and approved by University Cabinet. Negotiations with insurer completed, and spouse coverage proposal ready for FY 2026 implementation, subject to the approval of the company. | HR retention metrics (turnover %, exit interview themes). Comparison of benefits vs. peer institutions. | Budget for research, actuarial analysis, and the potential incremental cost of new benefits. | Completed staff salary benchmarking; a new Administrative salary scale has been prepared, approved, and implemented. Additional benefits have been approved, such as, an annual airfare ticket for international employees to their Home of Record; educational benefits including free tuition for degree programs for employees and their children studying at AUK. Meetings with ASIA Company will be scheduled soon to negotiate spouse enrollment in the medical plan.
Devise more initiatives dedicated to the acculturation of international faculty and staff | HR | To ensure that every international hire experiences a smooth, supportive, and culturally aware transition to AUK and Kurdistan, accelerating their engagement and productivity. | Completely redesign the onboarding program with input from Administrative Units and Colleges. Launch interactive HR Chatbot to serve as 24/7 relocation and HR policy assistant. Develop and deliver departmental SOP workshops (tax, benefits, IT systems, local culture). Assign peer mentors/buddies for each international hire during the first semester. | Short-term: New orientation framework rolled out, with 100% of international hires participating. Long-term: Reduced attrition of international hires and higher onboarding satisfaction scores (>85%). | All international hires from spring 2026 onward onboarded using the new model, chatbot active, and workshops completed. | New hire onboarding survey scores; retention rate of international faculty/staff after 6 and 12 months; participation and feedback from orientation workshops. | HR facilitation hours, chatbot development and maintenance budget, workshop materials, cross-unit staff participation. | Most onboarding and acculturation steps have been implemented; all units have been informed. Units will develop and adopt SOPs for onboarding with HR monitoring implementation starting next semester. The HR chatbot is also being trained to support onboarding, relocation, and HR policy guidance.
Fully implement a program of capacity-building workshops/trainings reflecting the needs documented in the faculty and staff performance evaluations | CAPA | To enhance the competencies, productivity, and professional growth of faculty and staff by implementing targeted, needs-based capacity-building workshops and training programs, aligned with findings from annual performance evaluations. | Analyze faculty and staff evaluations to identify common performance gaps or development areas; provide regular workshop on topics matched to the priority needs identified; update training offerings based on new performance evaluation data, feedback, and emerging institutional needs. | Short-term: Training plan developed and implemented; at least 3 capacity-building workshops held annually for both faculty and staff; at least 80% of employees participate in all training sessions per semester; feedback collected showing improvement in knowledge and skills in key areas. Long-term: All faculty and staff participate in ongoing professional development annually; improved institutional productivity; enhanced staff retention, employee satisfaction, and institutional reputation. | List of trainings for the year developed based on evaluation data; at least 3 workshops/trainings implemented, targeting high-need areas; 80% or more of faculty and staff attend; post-training feedback collected and analyzed for follow-up actions; integration of training participation into academic review systems initiated. | Number of workshops delivered; attendance rates; number of repeat participants; participant satisfaction surveys; workshop impact assessments (self and supervisor-reported); improvement in relevant performance indicators. | Training coordination; internal and external trainers; logistics. | CAPA carried out training series for staff development in teamwork and motivation. Will continue the process that will lead to a "Certificate in Leaderhip and Management."
Fully implement a program of capacity-building workshops/trainings reflecting the needs documented in the faculty and staff performance evaluations | HR | To enhance the competencies, productivity, and professional growth of faculty and staff by implementing targeted, needs-based capacity-building workshops and training programs, aligned with findings from annual performance evaluations. | Analyze faculty and staff evaluations to identify common performance gaps or development areas; provide regular workshop on topics matched to the priority needs identified; update training offerings based on new performance evaluation data, feedback, and emerging institutional needs. | Short-term: Training plan developed and implemented; at least 3 capacity-building workshops held annually for both faculty and staff; at least 80% of employees participate in all training sessions per semester; feedback collected showing improvement in knowledge and skills in key areas. Long-term: All faculty and staff participate in ongoing professional development annually; improved institutional productivity; enhanced staff retention, employee satisfaction, and institutional reputation. | List of trainings for the year developed based on evaluation data; at least 3 workshops/trainings implemented, targeting high-need areas; 80% or more of faculty and staff attend; post-training feedback collected and analyzed for follow-up actions; integration of training participation into academic review systems initiated. | Number of workshops delivered; attendance rates; number of repeat participants; participant satisfaction surveys; workshop impact assessments (self and supervisor-reported); improvement in relevant performance indicators. | Training coordination; internal and external trainers; logistics. | Launched institution-wide training sessions for faculty and staff on common development needs (Effective Communication in the Workplace, Mentoring and Coaching, Emotional Intelligence). In collaboration with the General Counsel, delivered institutional orientation/compliance trainings (Conflict of Interest and Commitment, Sexual Harassment, and related topics). Finalized the 2025 evaluation reporting, and targeted capacity-building trainings will be delivered based on identified recommendations, internally or externally, depending on the training.
Leverage relationships with U.S. universities for staff and faculty capacity-building | VPAF, OGM | To strengthen institutional capacity by engaging faculty and staff in professional development opportunities with partner U.S. universities - aim is to enhance teaching quality, research productivity, administrative efficiency, and alignment with international higher education standards. | Continued applications with DOS to ensure sustainability and scalability of partnerships with selected U.S. universities. Possible activities: Joint training initiatives, faculty exchanges, virtual workshops, mentorship programs, etc. | Short-term: Faculty and staff participate in structured training sessions and exchange visits with U.S. universities. Long-term: AUK cultivates a pool of faculty and staff with enhanced expertise grounded in U.S. best practices. | At least 30% of academic and administrative staff have participated in capacity-building initiatives with U.S. partners, with measurable improvements in teaching, service delivery, and research collaboration. | Impact is measured through participant feedback, peer evaluations, post-training performance assessments, and the number of active collaborations sustained with U.S. universities. | DOS funded travel, training fees, and visiting faculty stipends; OGM to coordinate with U.S. universities; and administrative support for MoUs and partnership logistics. | Collaboration with JMU, WSU, Align Nursing Education, and Higher Education Consulting. Faculty receive training to support and advance the accreditation process. Administrative units—OC, HR, CSD, IT, ARD, and OIEP—worked with JMU. One of the most recent collaborations involved JMU and OIEP in the establishment of a data warehouse.
7. To strengthen AUK’s communications for the purpose of promoting the University’s brand identity and visibility regionally and internationally
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Develop mechanisms to efficiently document and archive events at AUK | OC | To create a sustainable, centralized, and easily accessible institutional archive that preserves the history of AUK events, strengthens institutional memory, and supports branding, accreditation, and fundraising efforts. | Partner with IT to design and set up a secure, centralized server dedicated to OC’s archival needs; define folder structures, naming conventions, and metadata standards for event documentation (photos, videos, publications, media coverage); migrate existing event documentation (2014–present) from scattered drives and personal devices onto the new server; establish a standard operating procedure (SOP) for uploading and categorizing all future events in real time. | Short-term: Centralized server created, migration of legacy files begins, SOP drafted and staff trained. Long-term: Fully organized and searchable archive available for internal stakeholders, providing reliable institutional memory and supporting external reporting and communications. | 100% of legacy event documentation migrated to the centralized server; fully functional, searchable archive with metadata tagging system; OC routinely archiving events within two weeks of occurrence. | Server audit reports showing percentage of files migrated; compliance rate with SOP (tracked quarterly); internal user feedback on ease of access and search functionality; random quality checks of archived materials for completeness and accuracy. | IT for server setup and ongoing maintenance; OC staff time for file migration and metadata tagging (may require student assistants for bulk upload); minimal fiscal investment (server space allocation, potential cloud storage subscription, metadata management tool if needed). | IT is working on the centralized data storage. OC staff were informed of the project and started organizing files. SOPs will be developed once ready to start setting up the storage.
Ensure that messaging is presented in all appropriate languages and that translations accurately communicate the intended meanings | OC | To achieve full linguistic accessibility of AUK’s core communications, ensuring that prospective students, donors, and the public can engage with AUK’s messaging in English, Kurdish, and Arabic with accuracy and consistency. | Phase 1: Present all social media content in three languages (English, Kurdish, Arabic). Phase 2: Translate selective high-impact pages on the University website for prospective students (Admissions, Scholarships, Colleges, Program pages). Phase 3: Translate donor-facing content (Giving page, digital newsletters). Maintain an approved glossary of institutional terminology in three languages to ensure translation consistency; implement internal review before publication to ensure cultural appropriateness and accuracy. | Short-term: Website translation plan completed, glossary finalized; student-recruitment-facing content (Admissions, Colleges, Housing) is fully available in three languages. Long-term: Donor and public-facing content is translated and kept up to date on an ongoing basis. | All phases completed for prospective student, donor, and public-facing content. SOP established to ensure all content remains current and updated in all three languages. | Content audit reports showing percentage of translated pages completed; tracking website traffic and engagement metrics for translated pages (compare pre- and post-translation); quality checks on translations against glossary/style guide. | OC staff; Work-Study translators; IT support for website integration of multilingual content. | Work study translators have created a glossary and translated the Academic and Admissions webpages. They will begin translating OSA content; OC staff will review. A multilingual website ahs not been technically finalized by the web vendor.
Publish newsletters, articles, and content across various platforms catering to various stakeholder groups | OC | To develop and deliver content specifically designed for key stakeholder groups—students, alumni, faculty, donors, and the public. | Develop an annual content calendar for newsletters, articles, and social media posts, targeting students, alumni, faculty, donors, and the public; produce high-quality written, visual, and multimedia content highlighting academic programs, research, events, achievements, and community initiatives; develop a platform-based strategy for social media, tailoring content type, format, and posting frequency to each platform to maximize engagement with specific target groups; distribute newsletters via email and website; share articles across social media, media partners, and other relevant platforms; monitor analytics, engagement metrics, and stakeholder feedback to optimize content strategy continuously. | Increased engagement from each target group measured through platform-specific metrics such as likes, shares, comments, click-through rates, and direct feedback; greater awareness of university initiatives, events, academic programs, and achievements among all key stakeholder groups. | Platform-based social media strategy fully implemented for all target groups; content available in Kurdish, English, and Arabic for all relevant stakeholder-facing channels; SOP for content creation, publication, translation, and platform-specific optimization fully operational; measurable increases in engagement and stakeholder satisfaction. | Platform-specific analytics for each stakeholder group; quarterly internal evaluations of content quality, distribution, and engagement trends; monitoring adherence to the content calendar and SOP. | Content writers, graphic designers, translators, social media managers; budget for digital platforms, design tools, and media promotion. | The first half of the University social media plan, and specifically the recruitment plan for AY 2025-2026, focused on informative and engaging content to reintroduce unique selling points of the university and its programs. The second half focuses on maintaining student-oriented content while producing messages from Deans, student and alumni, and interviews/opinion pieces from Faculty.
Develop a mechanism within the Office of Communications for quality control ensuring integrity, transparency, and accuracy across all messaging | OC | As per NECHE expectations, to ensure that all communications—internal and external—are accurate, consistent, and reflect AUK’s standards of integrity and transparency, thereby strengthening stakeholder trust and institutional credibility. | Develop and implement a written SOP for website updates, annual reports, catalogs, and content dissemination across all channels; implement a standardized review and approval process for all communications, ensuring compliance with the style guide and SOP; conduct periodic audits and feedback sessions to refine enforcement and training processes. | Reduced errors, inconsistencies, or miscommunications across publications; clear accountability and documented review process for all content; enhanced credibility and trust among internal and external stakeholders. | SOP for website updates, annual reports, catalogs, and content dissemination developed, implemented, and actively followed; tracking system shows adherence to style guide and SOP, with reduced errors. | Audit reports assessing style guide compliance across all content types; monitoring of review and approval tracking system. | OC staff to develop, maintain, and oversee the SOP for website updates, annual reports, catalogs, and content dissemination. | SOPs have been developed for website updates, annual reports, and catalogs, and have been communicated to relevant stakeholders. The next step is incorporating SOPs into relevant policies.
Design a process to prevent external online fraud | Legal Office | To ensure the authenticity of data/information and its sources, therefore, protecting AUK's reputation and its image to the public. | Regular review to identify vulnerabilities; implementing an automated monitoring system that analyzes unusual patterns and detects fraud; when fraud is suspected, conduct investigation to identify root causes and implement corrective measures; conduct reviews after any incident to update controls. | Short-term: Protect AUK website and its social media platforms from unauthorized access; monitor the content of the AUK's website and its social media platforms to ensure information/date integrity, transparency, and accuracy; ensure only author(s) of data is authorized to amend or delete the published data on the website or the social media platforms. Long-term: Protect AUK's reputation and its image to the public. | Deploy an automated monitoring system that analyzes unusual patterns and detect fraud. | Percentage of fraudulent websites and social media platforms; number of online reviews; number of investigations. | OC, IT, Automated monitoring system. | No documented cases of unauthorized or fraudulent websites affecting AUK were identified; consequently, there were no confirmed incidents requiring investigation, reporting, or remedial action. In the second half of the year, an automated monitoring system will be launched.
Publish more narratives that highlight faculty, staff, students, and alumni, as well as institutional success stories | OC | To showcase the achievements and experiences of AUK’s community and institutional milestones to strengthen engagement, build pride, and enhance the University’s reputation locally, regionally, and internationally. | Identify compelling stories of faculty, staff, students, alumni, and institutional initiatives through interviews, surveys, and internal submissions; produce high-quality written, visual, and multimedia content; develop a content calendar specifically for narratives and success stories; publish narratives across multiple channels: newsletters, website, social media, and media partners; collect and monitor feedback and engagement to refine storytelling approaches and topics. | Increased visibility of AUK’s achievements and community successes; strengthened relationships with students, alumni, faculty, staff, and external stakeholders; enhanced brand reputation and institutional credibility; increased bank of narratives for ongoing use in marketing and communications. | Regular publication of faculty, staff, student, alumni, and institutional narratives according to the content calendar; observable increases in engagement metrics; stakeholders report higher awareness and appreciation of University achievements. | Analytics on newsletter readership, website visits, and social media engagement for each narrative; stakeholder feedback via surveys and focus groups; periodic internal review meetings to assess storytelling effectiveness and identify new story opportunities. | OC, Alumni Relations, College Managers. | Student testimonials are captured during campus events through interviews. Alumni success stories are shared through the monthly newsletter and incorporated into the Office of Advancement's campaigns. One staff or faculty highlight is shared per month through the newsletter, and their achievements are published as news articles and on LinkedIn, including conference participation, research publications, etc.
8. To establish and maintain high-level international standards and principles for transparency and effective control in financial operational infrastructure
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Update policies related to SAP utilization for recording, authorizing, and reporting | Finance | To achieve greater efficiencies in the annual financial audit procedure and ensure compliance with international standards and principles of transparency. | Risks in financial processes are identified and addressed via policies including: cash handling, fixed assets capitalization and disposal, currency exchange, student balances and installments, advance, and month/year end policies. Address financial policies and procedures with the unit heads; create handouts and SOPs; adhere to GAAP standards; internal control mechanisms in place; implementation of an ERP system (SAP); proper record retention. | Provide AUK with professional and financial transparency to achieve its mission and accreditation and external audit expectations. | Policies to be approved by BoT. | KPIs: Number of policies that adhere to GAAP Standards; percentage of completion for implementation of ERP System . | Finance with External Auditors. | Once full implementation and trainings are completed; policy needs will be drafted.
Develop and train staff on financial reporting methods for different stakeholders at month-end, quarter-end, and year-end using SAP data | Finance | To build staff capacity in producing accurate, timely, and stakeholder-focused financial reports while ensuring compliance with international standards. | Conduct SAP-based financial reporting training; create user manuals and training materials; simulate reporting cycles; provide refresher training at quarter-end and year-end; develop cross-check templates. | Short-term: Staff proficient in SAP financial reporting. Long-term: Timely, error-free reports for management, donors, and external auditors. | Team is able to generate and articulate accounting reports | KPIs: % of staff certified on SAP reporting; reduction in reporting errors; timeliness of monthly/quarterly reports. | EY, external training providers. | Initial training was set by EY in first week of December 2025, but EY cancelled as they do not have the capacity for training. Looking for an institution that gives technical accounting training.
Develop a payment gateway (domestic and international) for students, parents, and donors | Finance | To establish a modern and trustworthy online payment infrastructure that enables students, parents, and donors to pay securely from anywhere, reducing reliance on cash handling. | Design and implement a payment portal integrated with SAP; partner with banks/payment processors; ensure multi-currency support; launch donor payment channel; provide training and user guidelines. | Short-term: Online payment solution launched. Long-term: Increased adoption, reduced manual transactions, and secure, efficient payment flows. | Operational Payment Platform. | KPIs: % adoption by students and donors; transaction success rate; user satisfaction. | Finance with Bank. | AUK has opened a new bank account with NBI who has reliable payment processing means. Once the payroll disbursement process is fully implemented and is reliable, AUK can consider NBI for student and donor payments.
Collaborate with banks in the development of student loans and employee loans | Finance | To expand financial access for students and staff through structured loan programs while ensuring transparency and compliance. | Negotiate agreements with banks for loan products; create eligibility criteria; integrate loan repayment with payroll/SAP; provide awareness sessions for students and employees. | Short-term: Loan products available and communicated to stakeholders. Long-term: Improved financial access and reduced dropout/staff turnover due to financial stress. | Loan programs operational and first batch of students/employees enrolled. | KPIs: Number of loan agreements signed; % uptake by students and employees; repayment compliance. | Finance with Bank. | Obtained a student loan offer from Iraqi Development Bank, yet will request offers from SafeHome, NBI, and RT and decide which to present to BoT.
Hire an internal auditor to strengthen the University’s internal control and compliance framework | VPAF | To strengthen governance, compliance, and accountability across all university operations. | Position advertised and person hired through a transparent recruitment process. Initial audits focus on high-priority areas. Findings are reported to management and the BOT, and follow-up actions are tracked to ensure improvements. Regular audit cycles are institutionalized, creating a continuous improvement loop. | Short-term: auditor recruited; first cycle of audits completed. Long-term: University develops a culture of accountability with systematic risk mitigation and strengthened internal controls. | Internal auditor conducting periodic audits with actionable recommendations. | Audit reports; the rate of implementation of recommendations; feedback from management and BOT. | Cost of new position. | No suitable candidate has been identified to date. Alternative recruitment measures will be implemented to attract a qualified candidate pool.
Utilize the Sustainability Formula to evaluate efficiency across academic and non-academic units, ensuring alignment with institutional fiscal guidelines | VPAF | To apply a systematic framework that evaluates efficiency and sustainability across University units, ensuring alignment with fiscal guidelines and institutional goals. | The Sustainability Formula framework will be refined and finalized; data collection begins, followed by pilot testing for academic programs and revenue generating units; formula is integrated into the annual planning cycle, guiding decision-making. | Short-term: Pilot testing of formula completed. Long-term: Sustainability Formula is used annually as a central tool for planning and budget alignment. | Formula is applied across the academic and administrative units, with preliminary results feeding into the institutional planning cycle. | Progress is measured through the completion of the annual sustainability calculation and the use of results to guide institutional decision-making. | SAP Data | The sustainability formula has been refined, and a pilot calculation was conducted for AY24. Both the executive and user dashboards have been completed. In spring, a calculation will be conducted for AY25, along with the development of the projection model. Results will be presented to the BoT.
Explore opportunities for public-private-industry partnerships that can generate income for the University, internships for students, and employment for alumni | Advancement, Legal Office | To build strong public-private industry partnerships that generate sustainable income and benefits for students and the University. | Develop partnership packages; engage key industry players; launch projects such as sponsorships and student placements. Build on successes to expand into long-term collaborations that generate income and employment opportunities. | Short-term: Secure new sponsorships, internship placement, and pilot collaborations. Long-term: Establish sustained income streams, expand industry networks, and create ongoing pathways for student and alumni employment. | In process of negotiating one active partnership. | Number of active partnerships; revenue generated; student internships; alumni employment. Partner feedback, regular reports, and quarterly reviews will help evaluate the outcomes of the initiatives. | N/A | There is ongoing exploration of a partnership with the Kurdistan Foundation on projects of mutual interest. Partnership with Stirling School aims to enhance and secure student recruitment opportunities. Partnership with Pling Energy Company is secured and continues to provide funding for AUK events.
9. To promote advancement activities and fundraising to increase revenue streams to the University and ensure resources to sustain and grow the institution
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Fully implement the Alumni Association, including Chapters in Kurdistan and internationally | Alumni Relations | To establish a sustainable Alumni Association with an active Executive Committee and functional members, fostering engagement, community building, and support for AUK. | Launch the Executive Committee and appoint functional committee members; develop and adopt bylaws defining roles and responsibilities; establish at least one operational chapter in Kurdistan and explore chapters abroad, including alumni networks among friends and peers; provide communication platforms (newsletters, website, social media) to connect alumni locally and globally. | Short-term: Fully functioning Association with active leadership, adopted bylaws, and at least one operational chapter implementing programs. Long-term: Expansion to international chapters, sustained alumni engagement, and strong alumni–university partnerships. | Local chapter fully operational; bylaws approved; inaugural Association events conducted; international outreach in progress. | Meeting minutes; membership tracking; event attendance; alumni surveys; feedback from chapter leads. | Committee volunteers, budget for events and communications. | The Executive Committee and functional committee members of the Association have been appointed; bylaws developed and approved. Chapter leads for Duhok and Erbil cities have been selected. The Alumni Association has been holding monthly online meetings. One alumni activity was conducted in December in the form of an online alumni dialogue session. A one-year Alumni Association implementation plan has been developed. Alumni expertise highlights are in progress, with content development underway and video recording scheduled for February.
Expand the alumni engagement plan to promote the Alumni Association, alumni success stories, and testimonials | Alumni Relations | To strengthen alumni engagement, connection with AUK, and visibility of the Alumni Association locally and internationally. | Implement an Alumni Engagement Campaign by sharing alumni stories and testimonials, developing and applying Association branding, promoting activities, and enhancing engagement through social media and creative content. | Short-term: Increased awareness of the Alumni Association among alumni and the wider community; higher engagement in Association programs and initiatives; enhanced online visibility. Long-term: Increase awareness of the Alumni Association and its opportunities, expand alumni engagement in events and initiatives, showcase alumni achievements, strengthen alumni pride and identity, encourage contributions and advocacy, and ensure sustainable growth and visibility locally and internationally. | Increased sharing of alumni stories, higher engagement in Association programs, and expanded online presence. | Alumni engagement in programs and initiatives; attendance at events; stories shared; social media metrics; website analytics; feedback surveys; recognition of the Alumni Association. | Media production support; modest budget for content creation and campaigns. | Alumni Association was officially launched during the Annual Alumni Reunion, with participation from over 165 alumni. Post-event alumni surveys were circulated to gather feedback and perceptions related to the Alumni Association. Branding for the Alumni Association and the establishment of dedicated social media accounts are in progress. Website updates to support Alumni Association visibility are underway, including a recorded video message from the President of the Alumni Association. As part of the alumni engagement campaign, alumni success stories and testimonials are currently being collected and shared through the Office of Comunication's available channels.
Expand prospect research to identify more private and international organizations with commitments to supporting educational organizations | Advancement | To build a strong list of potential partners and donors to support AUK. | Expand prospect research to include more private and international organizations; initiate outreach; secure new sponsors while strengthening relationships with current partners. | Engage international and local supporters; improve branding and marketing; activate endowment to facilitate international support. | Expanded prospect pipeline; initiated outreach to new organizations; secured initial sponsorships; strengthened systems for donor engagement. | Tracking the growth of the prospect pipeline; outreach and engagement with new and current sponsors; number of proposals submitted and commitments secured; effective use of systems to monitor and manage donor relationships. | Advancement staffing. | During the first half of the year, prospect research was broadened to identify new private and international organizations.
Work with AUKE in fundraising efforts and devise a strategy for the investment of funds | Advancement, Finance, AUKE | To build sustainable financial resources for AUK by collaborating with AUKE on coordinated fundraising initiatives and establishing a strategic investment plan that maximizes the long-term growth and impact of endowment funds. | Appoint a new chair for AUKE to lead fundraising and outreach efforts; recruit additional AUKE members to expand fundraising capacity and networks; finalize AUKE bylaws to formalize governance and strengthen accountability; develop and approve an annual calendar of meetings and fundraising activities; mobilize AUKE leadership and members to actively participate in donor cultivation and fundraising campaigns; design a clear investment plan for AUKE funds, whether through external financial companies or internal strategies, to ensure long-term growth and impact. | Short-term: More members recruited; annual AUKE calendar launched with consistent meetings and activities; initial investment strategy outlined. Long-term: AUKE functions as an active, structured fundraising body with strong leadership; international donor base expanded through AUKE outreach and events; sustainable investment plan implemented, ensuring steady growth of endowment and scholarship funds; significant increase in annual fundraising totals and diversified revenue streams. | Year 1: Establishing infrastructure. Years 2 and 3: Beginning of fundraising efforts. | Track annual fundraising totals against campaign goals; monitor new donors and donor retention; evaluate AUKE Board meetings; review creation and adoption of investment policy; collect feedback from AUKE members, donors, and partners; benchmark investment returns against targets and industry standards. | Dedicated Advancement staff to coordinate AUKE fundraising activities; Endowment Fund Manager. Increased budget allocation for AUKE fundraising events, donor engagement activities, and fund management fees. | AUKE endowment currently stands at approximately USD 2.1 million. Two more board members have been appointed with relevent expertise and broader diaspora representation; they will assist in evaluating investment options to improve returns ahead of identifying professional endowment managers. Fundraising efforts will prioritize corporate and philanthropic partnerships, enhanced marketing through an Annual Impact Report.
Continue to enhance relationships with relevant government agencies to secure and maintain committed funding from the KRG, including government-sponsored scholarship funds | Advancement, Legal Office | To build and sustain strong, strategic relationships with key government agencies, ensuring ongoing support and funding from the KRG, including government-sponsored scholarships. | Identify the relevant government agencies and key decision-makers; establish regular communication to share the University's priorities and impact; presenting well-prepared proposals for funding and scholarship programs; maintaining ongoing engagement through updates, reporting, and follow-ups to strengthen trust and ensure support. | Short-term: Establish contact; secure initial funding commitments (regular payments for receivables); build a system for tracking engagement and reporting. Long-term: Maintain sustained relationships that ensure consistent KRG funding. | Strong relationships with relevant government agencies; secured ongoing KRG funding and scholarship commitments (Martyr and Political Prisoners Scholarships, Scholarship for Excellence); implementation of a reliable system for tracking and reporting government-supported programs. | Number of government agencies engaged; funding and scholarship commitments secured; consistency of follow-up communications; effectiveness of systems used to monitor and report government-supported programs. | N/A | Successfully maintained special status funding.
10. To foster a culture of assessment and data-based decision-making meeting the expectations of institutional and program-level accreditation standards
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Promote the efforts of the Policy Task Force to optimize policy management and monitoring | OIEP | To achieve a transparent, efficient, and sustainable policy management framework where all policies are current, accessible, and consistently applied, each with a clear timeline, communication plan, and defined measurements of success to enable continuous review and improvement, while also ensuring proactive action is taken to address NECHE comments and feedback. | Build awareness and understanding of the Policy Task Force and its charges through a campus-wide orientation; conduct work-group sessions to actively engage stakeholders in drafting, reviewing, and improving policies, ensuring transparency and shared ownership; act as a liaison across divisions and units to promote consistency, reduce duplication, and ensure a collaborative approach to policy formulation; address all comments from stakeholders together with issuing units, and review draft policies for clarity, coherence, and institutional fit prior to their submission to the formal policy approval channels, leaving the voting matters to the University Cabinet; support and help monitor the development of clear, actionable implementation plans for approved policies, ensuring that responsibilities, timelines, and follow-up mechanisms are defined. | Short-term: Focus on inclusion and awareness by training and actively involving stakeholders in the policy process, while at the same time, prioritize reviewing and updating policies that are most urgent due to outdated processes or other critical needs. Long-term: Achieve full institutional adoption of the policy management system, leading to improved compliance and enhanced policy coherence and consistency across the institution. | At least 40% of university policies reviewed, updated, and uploaded; monthly policy monitoring reports shared with leadership; increased policy communication and awareness through the implementation of policy plans, along with more data generated from policies to support continuous improvement. | Number/percentage of policies reviewed and updated annually; faculty/staff feedback through surveys on policy clarity and accessibility; number of policy changes implemented based on the data collected from policies. | N/A | To date, 23 policies have been completed. In parallel, the Policy Task Force has established, participated in, and overseen meetings with issuing units to support both the drafting and implementation of policies, including detailed reviews of implementation plans with all relevant stakeholders, while maintaining a continuous feedback loops with stakeholders to ensure that comments are fully considered, incorporated, and reflected in final policy outcomes. In addition, a campus-wide assembly was held during Fall 2025 to build awareness and understanding of the Policy Task Force and its charges, with an additional campus-wide assembly planned for the current semester.
Implement strategies to enhance data collection, archiving, and analysis, as well as data usage in institutional decision-making | OIEP | To build a culture of evidence-based decision-making supported by reliable and accessible data. | Standardize data collection templates; conduct training on data use in planning; establish archiving protocols for institutional records. | Short-term: Improved data consistency and availability. Long-term: Data-driven decision-making across units. | Standard templates implemented; 90% of units reporting data on time. | Compliance tracking of data submissions; annual OIEP audit of data quality. | N/A | Established data governance policies and proceduers to ensure accuracy, consistency, and reliability; compiled standardized definitions of terms; training staff and administrators on how to interpret and use data effectively. The 2024–25 calendar was established and followed for census and other reports. The calendars have been revised after the first-year cycle; institutional dashboards have been updated accordingly.
Develop the Data Warehouse, including identifying an IR Consultant to map the data flows needed for the warehouse | OIEP, IT | To create a centralized data warehouse to support institutional reporting, planning, and accreditation. | Identify and fund IR consultant who will map data flows across units; work with incoming faculty to build system for data integration. | Short-term: Data flows mapped and pilot phase completed. Long-term: Fully functional data warehouse supporting dashboards. | Consultant hired; initial data warehouse operational. | Milestone tracking of implementation; usability testing with users on unit level; implementation of dashboards for institutional referencing. | External Consultant fees, cost for the cloud/software. | JMU identified consultant to conduct the data mapping; consultant visited campus in November 2025. The software engineer started the work viturally in January 2026. A data manager started January 2026.
Fully implement KPIs for the measurement of progress on Institutional Goals within the Strategic Plan | OIEP | To ensure effective monitoring of institutional progress toward strategic goals. | Finalize KPI definitions with units; collect and validate KPI data annually; publish KPI dashboards for leadership for decision-making and effective planning. | Short-term: KPIs validated and reported. Long-term: Continuous use of KPIs in planning and resource allocation. | 75% of institutional KPIs implemented and reported annually. | KPI tracking dashboards; annual performance reports. | Dashboard software maintenance. | OIEP has completed one cycle of reporting to the BoT. Feedback received and adjustments to reporting protocols to be made in AY2025-6.
Collect data and evidence for the assessment of AUK’s 5-year strategic plan in preparation for the plan’s closeout in Summer 2026 | OIEP | To implement and execute a system for the comprehensive evidence-based evaluation of the effectiveness of the 2021–2026 Institutional Strategic Plan. | Gather reports and evidence from all units; analyze progress toward strategic goals; draft the final closeout report. | Short-term: Data collection complete. Long-term: Published strategic plan closeout report with recommendations for next cycle. | Closeout report finalized and shared with BoT. | Feedback from leadership. | N/A | The close out report is scheduled for drafting in Spring 2026.
11. To support institutional accreditation activities in order to ensure the optimization of the process and timeline
Action Priority | Responsible Unit | Objective (what you hope to accomplish long-term) | Tactics (the step-by-step initiatives to be implemented) | Desired Outcomes/Outputs (short-term and long-term for tactics needing multiple years to complete) | Expectation of Progress by July 31, 2026 | Assessment Mechanisms to Gauge Progress | Human and Fiscal Resources Needed for Implementation of Tactics | Mid-year Updates | End of year Updates
Ensure all academic and administrative units participate in the institutional accreditation efforts | OIEP | To achieve and maintain institutional accreditation through full engagement and compliance across all units. | Communicate accreditation requirements to all units; provide workshops on evidence collection and reporting; follow the reporting calendar for institutional assessment and data collection; assign unit-level liaisons for data submission and progress monitoring; conduct periodic internal reviews to ensure progress with the projections. | Short-term: All units understand their roles, provide timely reports, and submit evidence. Long-term: Successful completion of accreditation self-study and achievement of institutional accreditation. | Units demonstrate active participation in accreditation reporting; evidence compiled and ready for submission in the self-study report. | KPI: Tracking of unit submissions against reporting calendar; 80% of unit submissions received complete and on-time. | Participation of unit liaisons (time commitment); administrative support for documents and communication. | Institutional planning is continuously monitored, with updates and progress regularly reported.
Communicate NECHE processes and expectations to the campus community and various publics | OIEP, President | To build a shared understanding of NECHE accreditation standards and processes on campus and regionally. | Develop and distribute clear messaging for communications; host campus-wide assemblies/workshops to explain NECHE standards and updates on the progress; provide regular updates to the BoT and external stakeholders; incorporate accreditation updates into existing council and committee meetings. | Short-term: Faculty, staff, and students are aware of NECHE timelines. Long-term: A culture of continuous improvement and accountability that supports successful accreditation. | At least 1 campus-wide assembly held per semester. | Attendance and participation records from workshops/assemblies (70% attendance); surveys of campus community awareness and understanding with 70% of employees reporting awareness and understanding. | N/A | NECHE accreditation progress and planning were presented during an Assembly in August to the AUK community, and was further discussed and reinforced during the Strategic Planning sessions. Then, in the Board Retreat in November, 2025.
Establish workgroups and guide efforts in the writing of a Self-Study for the mid-point candidacy evaluation for NECHE | OIEP, President | To submit a comprehensive and evidence-based Self-Study that demonstrates AUK’s progress, compliance with NECHE standards, and readiness for the mid-point candidacy evaluation. | Form NECHE workgroups aligned with accreditation standards; assign standard chairs and members from across academic and administrative units; provide training for writing and evidence collection; set a detailed timeline with milestones for draft submissions; conduct reviews and feedback sessions before final compilation. | Short-term: Organized workgroups actively drafting sections based on data and supporting evidence. Long-term: A completed, high-quality Self-Study report submitted to NECHE on schedule. | Workgroups established and operational by end fall; at least 100% of Self-Study sections drafted and internally reviewed by mid-spring semester; Self-Study submitted in June. | Completion of the SSR. | Workgroups composed of faculty and staff representative of all academic and non-academic units. | In October 2025, working groups were established for each accreditation standard, comprising representatives from across the AUK community to ensure broad stakeholder engagement. Clear guidelines were provided to these groups regarding data collection and documentation for the data workroom. OIEP and Provost attended NECHE Conference in December. The revision of NECHE standards will require additional sessions to the campus in Spring and a redesign of the workgroups and their charge.